## Sheet1
Task Name | Project name | Assignee | Estimated Time (min) | Actual Time (min)
documentation - create a library text file | Project 1 | blakejesse2022 | 15 | 5
Create graph of actual versus estimated time for coding | Project 1 | michael buckendahl
test - play through testing | Project 1 | Cole Charpentier | 20 | 45
view.py - welcome screen bomb too few too many | Project 1 | C. Cooper | 30 | 30
fix - view.py - flags remaining in wrong spot | Project 1 | michael buckendahl | 10 | 10
Document - Revamp meeting log template | Project 1 | Cole Charpentier | 20 | 10
everything - Remove print statements | Project 1 | Cole Charpentier | 20 | 15
app.py - update main loop to render welcome screen | Project 1 | michael buckendahl | 60 | 30
documentation - create meeting log | Project 1 | Cole Charpentier | 5 | 6
Document - Create pygame info document | Project 1 | Delaney Gray | 90 | 90
Canvas - check the work of Assignment 1 | Project 1 | michael buckendahl | 25 | 20
Canvas - Assignment 1 | Project 1 | C. Cooper | 60 | 30
board.py - Create handle_first_click function | Project 1 | C. Cooper | 10 | 45
board.py - Create reveal function | Project 1 | blakejesse2022 | 90 | 180
board.py - Create check_win, reveal_all_mines, toggle_flag functions | Project 1 | Cole Charpentier | 90 | 80
view.py - modify draw_board() to display outcome | Project 1 | Delaney Gray | 30 | 20
app.py - Create a skeleton loop for the main game | Project 1 | blakejesse2022 | 60 | 60
Document - Create project architecture document | Project 1 | michael buckendahl
Document - Create Read.me for the github repo | Project 1 | C. Cooper | 30 | 30
Document - Create Requirements document | Project 1 | Cole Charpentier
view.py - Create a welcome screen | Project 1 | Delaney Gray | 60 | 60
app.py - Update the main game loop | Project 1 | C. Cooper | 30 | 30
view.py - use pygame to draw the game board | Project 1 | Delaney Gray | 60 | 90
board.py - Create BoardGame class skeleton | Project 1 | michael buckendahl | 120 | 60
Config.py - Define constants for the project | Project 1 | michael buckendahl | 30 | 60
main.py - fix an error printing out incorrect game status | Project-2 | michael buckendahl | 45 | 50
main.py - implement the 1-2-1 rule in the hard AI | Project-2 | C. Cooper | 20 | 20
main,py - add function for AI to uncover move | Project-2 | Cole Charpentier | 15 | 15
main.py - add mode and difficulty to configure | Project-2 | Cole Charpentier | 20 | 15
main.py - update play function to handle new modes | Project-2 | Cole Charpentier | 45 | 45
main.py - Implement Grid Size feature | Project-2 | Delaney Gray | 120 | 210
main.py - implement medium AI | Project-2 | blakejesse2022 | 60 | 180
main.py - implement getSafeCell | Project-2 | C. Cooper | 45 | 45
main.py - implement canBeMine | Project-2 | C. Cooper | 45 | 45
main.py - implement easy AI | Project-2 | Cole Charpentier | 30 | 25
main.py - implement a score | Project-2 | michael buckendahl | 150 | 150
Create the Sprint 2 Requirements Stack | Project-3 | C. Cooper | 15 | 15
Create the Sprint 1 Requirements Stack | Project-3 | C. Cooper | 15 | 15
Research the KU Class Search API | Project-3 | C. Cooper | 30 | 30
Create the Sprint 1 Requirements Artifact | Project-3 | blakejesse2022
Create the Architecture Document - Sprint 2 and 3 | Project-3 | Delaney Gray | 120 | 120
Create the Architecture Document - Introduction and Sprint 1 | Project-3 | Cole Charpentier
Implement Search Bar and Dropdown with Fake Data | Project-3 | michael buckendahl | 30 | 25
Setup Website Layout | Project-3 | michael buckendahl | 50 | 45
Create UML Component Diagram | Project-3 | michael buckendahl | 30 | 35
Create UML User Interaction Flow Diagram | Project-3 | blakejesse2022
Create UML Class Diagram | Project-3 | C. Cooper | 120 | 120
Learn React | Project-3 | C. Cooper | 45 | 60
Learn React | Project-3 | Delaney Gray
Learn React | Project-3 | Cole Charpentier
Learn React | Project-3 | blakejesse2022