## Requirements Stack
ID | Description | Story Points | Priority | Sprint Number
2.3 | The website should parse the API's response into the data format defined by the architecture | 8 | 4 | 2 | Legend
4 | The system should display Class Cards for the selected classes. Class Cards contain the class name, credit hours, instructor, and class length. Each class card should have a unique color | 5 | 6 | 2 | " | Some requirements have sub-points that give more detail about the required behavior of the system. A quotation mark (") indicates that the sub-requirement's complexity was included in the story points of the parent, and that the sub-requirement inherits the parent's priority.
4.1 | Cards should be rendered in the order they are added | " | " | "
4.2 | There shouldn't be a shift the layout when many class cards have been added (should be able to scroll) | " | " | " | S | Some large requirements were split into smaller component requirements which were then assigned their own story points. A 'S' indicates that the requirement has been split in this way and its complexity is represented by the story points of its components.
6 | The class cards should contain data from the selected courses | 2 | 8 | 2
7 | The system should display the currently-selected schedule, with the ability to rotate through all possible permutations if courses offer multiple times. | S | N/a | 2
7.1 | The schedule should display in a grid. It should display monday through friday across the top with 30 min sections from 8 am to 6 pm top to bottom. | 5 | 9 | 2
7.2 | The schedule should display Schedule Cards for each of the selected class-times. They should include course name, building name, room number, and time. | 5 | 10 | 2
7.2.1 | The schedule should place Schedule Cards at their corresponding days and time. | " | " | "
7.2.2 | If there are no possible schedules with the selected classes, the system should block schedule the and display a message. | " | " | "
7.2.3 | Each scheduled card is given a color corresponding to its class card. | " | " | "
7.3 | Under the schedule, the system should display a "no scheduled time" section for unscheduled classes. | 5 | 11 | 2
7.3.1 | Display unscheduled cards class info (just course name), if applicable. | " | " | "
7.3.2 | Each unschedule card is given a color corresponding to its class card | " | " | "
7.4 | Display total possible schedules at the top. Ex "1 of 55 Schedules" | 3 | 12 | 2
7.4.1 | User can rotate through premutations of the class times | " | " | "
7.4.2 | Include <Prev and Next> buttons to rotate through different permutations of the class times | " | " | "
8 | Implement an algorithm that finds all possible permutations of the selected classes. - Note when there are no possible schedules. | 5 | 13 | 2
8.1 | If the user pins a Schedule Card, only show permutations with the pinned section of that course. | 2 | 14 | 2
8.2 | The user should be able to 'block' certain times of the day in 30-minute blocks to prevent any classes from appearing in them in the class permutations. | 3 | 15 | 2
8.2.1 | When a slot becomes blocked or unblocked, the permutaion options should update to reflect that | " | " | "
8.2.1.1 | If there is already a valid permutation before a slot is unblocked, the currently selected permutation should not change even if more permutations become valid | " | " | "
8.2.1.2 | If there is no valid permutation and unblocking a slot creates one or more valid permutations, one of the now-valid permutations should become selected | " | " | "