## Sheet1
Requirement | Planned? | Status | Requirements Reference
7.2.1 | Yes | Completed - C. Cooper | ID | Description | Story Points | Priority | Sprint Number
7.2.2 | Yes | Completed - C. Cooper | 7.2.1 | The schedule should place Schedule Cards at their corresponding days and time. | " | " | 3
7.4 | Yes | Completed - Michael B | 7.2.2 | If there are no possible schedules with the selected classes, the system should block the schedule and display a message. | " | " | 3
7.4.3 | Added | Completed - C. Cooper | 7.4 | Display total possible schedules at the top. Ex "1 of 55 Schedules" | 3 | 12 | 3
8.1 | Yes | Completed - Blake J | 7.4.1 | User can rotate through premutations of the class times | " | " | 3
8.2 | Yes | Completed - Blake J | 7.4.2 | Include <Prev and Next> buttons to rotate through different permutations of the class times | " | " | 3
10 | Yes | Completed - Delaney G | 7.4.3 | The user can rotate through permutations using the arrow keys | " | " | 3
11 | Yes | Completed - Cole C | 8.1 | If the user pins a Schedule Card, only show permutations with the pinned section of that course. | 2 | 14 | 3
|  |  | 8.2 | The user should be able to 'block' certain times of the day in 30-minute blocks to prevent any classes from appearing in them in the class permutations. | 3 | 15 | 3
|  |  | 8.2.1 | When a slot becomes blocked or unblocked, the permutaion options should update to reflect that | " | " | 3
|  |  | 8.2.1.1 | If there is already a valid permutation before a slot is unblocked, the currently selected permutation should not change even if more permutations become valid | " | " | 3
|  |  | 8.2.1.2 | If there is no valid permutation and unblocking a slot creates one or more valid permutations, one of the now-valid permutations should become selected | " | " | 3
|  |  | 10 | The user should be able to pin and unpin classes through the UI | 3 | 17 | 3
|  |  | 10.1 | The user should be able to left-click on a schedule card to pin it to its current time | " | " | 3
|  |  | 10.2 | When a schedule card is pinned, it should show a pin icon in the top-right | " | " | 3
|  |  | 10.3 | The user should be able to unpin a schedule card by left-clicking it | " | " | 3
|  |  | 10.4 | All schedule cards displaying a common class section number should share their pinned status | " | " | 3
|  |  | 11 | The user should be able to block times through the UI, and should receive feedback from the UI for which times are blocked | 3 | 18 | 3
|  |  | 11.1 | The user should be able to block and unblock times by right-clicking on a time slot and dragging over any times they want to toggle the status of | " | " | 3
|  |  | 11.2 | The UI should darken out the time slots to reflect them being blocked. | " | " | 3